## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US01 | User Account Registration | As a user , I want to register an account so that I can apply for jobs | Must | 1 | User can enter username & password; System validates uniqueness; Account is created successfully; The account can be divieded into three types. | 3 | Basic system access function, must be completed first | 2026-04-01 | 2026-04-11
TA01 | TA Applicant Profile Creation | As a TA applicant, I want to create my applicant profile, so that I can provide my personal and academic information for future job applications. | Must | 1 | The applicant can enter basic personal information. The applicant can enter academic information such as major, year, and skills. The system can save the profile successfully. The applicant can edit the profile later. | 3 | Core function for TA applicants, depends on US01 | 2026-04-01 | 2026-04-11
TA02 | TA Job Browsing | As a TA applicant, I want to browse available jobs and submit applications, so that I can apply for suitable TA positions efficiently. | Must | 1 | The applicant can view a list of available jobs. The applicant can see key information such as module name, requirements, and deadline. The applicant can choose a job and submit an application. The system confirms that the application has been submitted successfully. | 5 | Basic job viewing function for TAs | 2026-04-01 | 2026-04-11
TA03 | TA Application Status Check | As a TA, I want to see application status so that I know results | Should | 2 | Status shows Pending / Accepted / Rejected in the application page correctly | 2 | Depends on TA job application function | 2026-04-11 | 2026-04-21
MO01 | MO TA Job Publishing | As a module organiser, I want to publish a TA job post, so that students can see the vacancy and apply for it. | Must | 1 | The module organiser can create a new job post. The job post includes module name, description, requirements, and deadline. The system saves and publishes the job successfully. The published job becomes visible to applicants. | 3 | Core recruitment function for MOs, depends on US01 | 2026-04-01 | 2026-04-11
MO02 | MO Application List Review | As a module organiser, I want to review the list of applicants for my job post, so that I can compare candidates efficiently. | Must | 2 | The module organiser can view all applicants for a selected job. The system shows applicant profile information. The system allows the module organiser to view each applicant’s CV. The applicant list is clearly linked to the correct job post. | 3 | Depends on MO job publishing | 2026-04-11 | 2026-04-21
MO03 | MO Applicant Selection | As a module organiser, I want to select suitable applicants for a TA position, so that I can recruit the best candidate for my module. | Must | 2 | The module organiser can mark or select an applicant. The selected result is saved by the system. The application status is updated after selection. Other non-selected applicants can be marked as rejected or pending. | 3 | Depends on application list review | 2026-04-11 | 2026-04-21
MO04 | MO Job Editing | As a MO, I want to edit a job so that I can update information | Should | 2 | Job can be deleted; It no longer appears in list. Job details can be changed and upgrade in the list. | 2 | Supplement to job publishing function | 2026-04-11 | 2026-04-21
AD01 | Admin TA Workload View | As an administrator, I want to view the overall workload of each TA, so that I can avoid assigning too much work to the same person. | Could | 3 | The administrator can view a list of TAs and their current workload. The workload information is clearly displayed. The system updates workload data when a TA is assigned to a job. | 5 | Core admin monitoring function, required by project | 2026-04-21 | 2026//5/2
AD02 | Admin All User View | As an Admin, I want to view all users so that I can manage them | Should | 2 | System displays all TA and MO accounts Admin can delete user; User data is removed | 2 | System management function for admin | 2026-04-11 | 2026-04-21